## Sheet1
Risk ID | Risk Description | Probability | Impact | Risk Level | Member In Charge | Response / Action Plan | Status
R1 | Google API connection issue prevents data retrieval or authentication during integration. | Medium | High | Major | Tran Son Viet | Mitigate – Check API key validity and quota; use mock data for testing; contact Google Cloud support if issue persists. | Closed
R2 | Incomplete code or missing functionality before submission deadline. | High | High | Critical | Akshay Krishna | Mitigate – Prioritize core features; allocate extra development sessions; assign backup developers for pending modules. | Open
R3 | Developer absent, causing task delays. | Medium | Medium | Moderate | Aishwarya Anand | Mitigate – Redistribute tasks; ensure proper documentation; maintain shared access to code and resources. | Closed
R4 | UI or usability issues discovered during user testing. | Low | Medium | Low | Shen Jia Cheng | Accept – Fix during final polishing phase; document known issues if time constraints prevent fix. | Closed