## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Project Proposal | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 7 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 8 | 7
2 | Use Case Model | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 7 | Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 6 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 7 | 7 | 7 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 9 | 7
3 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
5 | Finalize & Submit Lab 2 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
6 | System Requirements Specification | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 7 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 8 | 7
7 | Quality Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 7 | Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 6 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 7 | 7 | 7 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 9 | 7
8 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
9 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
10 | Finalize & Submit Lab 3 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
11 | Project Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 7 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 8 | 8 | 8
12 | Risk Management Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 3 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 3 |  | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 9 | 9 | 8
13 | Risk Management log | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.6667 | 4.5 | 3 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 4 | 5 | 4 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
14 | Back End Development | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 9.5 | 7 | Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 10 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 10 | 9 | 9 | 10 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 9 | 8 | 9
15 | Front End Development | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 10 | 9 | 7 | Aishwarya Anand, Akshay Krishna, Sen Jia Cheng | Whole team | Discussion | Yes | 7 | Happy | 8.8333
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 9 | 9 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
16 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
17 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
18 | Finalize & Submit Lab 4 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
19 | Design report on software maintainability | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 9 | 9 | 9 | 10 | 7.1667 | 7 | Aishwarya Anand | Whole team | Discussion | Yes | 7 | Happy | 9.1667
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 6 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
20 | Configuration Management Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 9 | 9 | 10 | 6.8333 | 7 | Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 8 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 6 | 7 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
21 | Change management plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.6667 | 4.5 | 7 | Akshay Krishna | Whole team | Discussion | Yes | 4 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 4 | 5 | 4 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
22 | Release plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 9 | 9 | 10 | 6.8333 | 7 | Sen Jia Cheng | Whole team | Discussion | Yes | 6 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 7 | 7 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
23 | Presentation Slides | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 9 | 9 | 10 | 5.5 | 7 | Aishwarya Anand, Akshay Krishna, Sen Jia Cheng, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 5 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 6 | 6 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
24 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
25 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
26 | Finalize & Submit Lab 5 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
27 | Test Cases Report | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | Aishwarya Anand, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 4 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
28 | Test Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.3333 | 4 | Akshay Krishna, Sen Jia Cheng | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 7 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 4 | 4 | 4 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
29 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
30 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
31 | Finalize & Submit Lab 6 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9

## Team Meeting Lab 1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Project Proposal | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 7 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 8 | 7
2 | Use Case Model | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 7 | Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 6 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 7 | 7 | 7 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 9 | 7
3 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
5 | Finalize & Submit Lab 2 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9

## Team Meeting Lab 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | System Requirements Specification | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 7 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 8 | 7
2 | Quality Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 7 | Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 6 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 7 | 7 | 7 | 8 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 9 | 7
3 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 5 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
5 | Finalize & Submit Lab 3 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9

## Team Meeting Lab 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Project Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 7.5 | 6.8333 | Aishwarya Anand, Sen Jia Cheng, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 7 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 7 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 8 | 8 | 8
2 | Risk Management Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 6.1667 | 3 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 3 |  | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 8 | 9 | 9 | 8
3 | Risk Management log | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.6667 | 4.5 | 3 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 4 | 5 | 4 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Back End Development | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 9.5 | 7 | Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 10 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 10 | 9 | 9 | 10 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 8 | 9 | 8 | 9
5 | Front End Development | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 10 | 9 | 7 | Aishwarya Anand, Akshay Krishna, Sen Jia Cheng | Whole team | Discussion | Yes | 7 | Happy | 8.8333
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 9 | 9 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9
6 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
7 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
8 | Finalize & Submit Lab 4 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9

## Team Meeting Lab 4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Design report on software maintainability | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 9 | 9 | 9 | 10 | 7.1667 | 7 | Aishwarya Anand | Whole team | Discussion | Yes | 7 | Happy | 9.1667
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 6 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
2 | Configuration Management Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 9 | 9 | 10 | 6.8333 | 7 | Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 8 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 6 | 7 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
3 | Change management plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.6667 | 4.5 | 7 | Akshay Krishna | Whole team | Discussion | Yes | 4 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 4 | 5 | 4 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Release plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 9 | 9 | 10 | 6.8333 | 7 | Sen Jia Cheng | Whole team | Discussion | Yes | 6 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 7 | 7 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
5 | Presentation Slides | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 9 | 9 | 10 | 5.5 | 7 | Aishwarya Anand, Akshay Krishna, Sen Jia Cheng, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 5 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 6 | 6 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 7 | 7 | 7 | 7
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
6 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
7 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
8 | Finalize & Submit Lab 5 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9

## Team Meeting Lab 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignees | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Aishwarya Anand | Akshay Krishna | Nguyen Phuong Linh | Sen Jia Cheng | Tran Son Viet | Vu Thao Nguyen
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited
1 | Test Cases Report | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | Aishwarya Anand, Vu Thao Nguyen, Nguyen Phuong Linh, Tran Son Viet | Whole team | Discussion | Yes | 4 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 8 | 8 | 9 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
2 | Test Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.3333 | 4 | Akshay Krishna, Sen Jia Cheng | Whole team | Discussion | Yes | 3 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 7 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 4 | 4 | 4 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
3 | Backlog | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.5 | 3.3333 | Akshay Krishna | Whole team | Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 5 | 5 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 2 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Internal Review & Proofreading | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 5 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 6 | 6 | 7 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 4 | 4 | 4 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 5 | 5 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 8 | 9 | 8
5 | Finalize & Submit Lab 6 Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | Aishwarya Anand | Whole team | Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 6 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 9 | 9 | 9 | 9